# ! 26.x System PCE Full

Plan: a manifest-driven offline Illumio PCE for Instruqt · Illumio Training · 6 October 2026

# Context

The existing ! 26.x System PCE lab (26x-course/System PCE, commit 3885d96) is frozen and stays as it is. It is valuable because it needs no magic link and no PCE back end.

The new lab, ! 26.x System PCE Full (slug 26x-system-pce-full), keeps the no-back-end model but makes far more of the Console menu clickable and realistic.

The overriding requirement is that it must be quick and cheap to update when the real PCE menus change. So the lab is generated from a captured description of the real PCE, not hand-coded page by page.

# Core idea: capture → manifest → generate

real PCE ──(capture script)──▶ pce-manifest.json ──(build)──▶ index.html ──▶ Instruqt

+ seed.json            ▲

│

overrides/ (bespoke pages: pairing, policy, terminals)

- Capture. A repeatable script logs into a real PCE and walks the sidebar. For every menu item it records the menu path, page title, breadcrumb, banner, tabs, toolbar buttons (with enabled/disabled state), filter placeholder, table column headers, detail-page sections and fields, and Add/Edit form fields. It also saves a few sanitised sample rows and one reference screenshot per page.

- Generate. The lab page is built from that manifest using a few generic templates. There is no per-page code for the 90% of pages that are lists, details and forms.

- Override. Only the pages a lab teaches get hand-written behaviour: Pairing and the terminals, Policies, and later Labels and Services. Overrides attach to a menu path, so they survive regeneration.

## Upgrade path when the PCE changes

- Re-run the capture script against a live PCE.

- git diff pce-manifest.json shows exactly what changed: new menu items, renamed columns, new buttons.

- Rebuild the lab page.

- Check only the overrides the diff touches.

- Push to Instruqt and GitHub.

A menu change becomes minutes of work rather than days.

# Components

All in a new folder: 26x-course/System PCE Full/.

| Part | What it is |
| --- | --- |
| capture/capture-pce.mjs | Playwright (headless Chrome) script, run with a fresh magic link in an environment variable (PCE_MAGIC_LINK=… node capture-pce.mjs). The token is never written to disk or git. Read-only: it only navigates and reads the page, and never clicks Save, Remove or Provision. |
| pce-manifest.json | Menu tree plus a description of every page (template type, title, banner, tabs, toolbar, columns, fields). Committed to git, so changes are easy to see with a diff. |
| seed.json | Sanitised sample data (labels, services, IP lists, workloads, …). No real tenant names or emails; those are replaced with lab values. |
| src/templates.js | Generic page renderers: list, detail, form, static view, blank-with-search and placeholder. |
| src/core.js | Shared store, sync between tabs, reporting to the lab server, and page routing. Reused from the existing lab. |
| overrides/*.js | Hand-built pages carried over from the existing lab: pairing, pairing profiles, terminals and the policy editor. |
| build.mjs | Assembles the manifest, seed, templates and overrides into one HTML page, then embeds it in the Instruqt setup script. |
| Track files | Copied from the existing lab with new identity. Same lab web server (port 8080), four tabs (Illumio Console, Linux, Windows, AIX), splash and video, check-script pattern, and challenges 01–03. |

# Scope

## Clickable and realistic (generated from the manifest)

- Segmentation, including Policy Objects

- Label Management

- Servers & Endpoints

- Quarantine

- Access

- Settings

- Support

## Fully working (add, edit and remove are saved and used elsewhere)

- Pairing Profiles and Workloads

- Policies

- Labels and Label Groups

- Services and IP Lists

These feed the policy rule pickers. For example, a new label or service appears in Sources, Destinations and Services.

## Static or reduced

- Dashboard and Cloud: the default screen, not clickable.

- Explore › Map: a blank area with only the search and filter boxes. No map is drawn.

- Insights (all pages), Explore › Traffic and Mesh: shown in the menu, but each opens a placeholder.

# Build order

- Scaffold the new track: copy, new identity, push. It behaves the same as the existing lab.

- Split the single page into source parts with a build step. The output must behave the same; prove it with the existing automated tests.

- Write the capture script. Run it once against a live PCE and review pce-manifest.json together.

- Write the generic templates and the manifest-driven sidebar. Every menu item becomes clickable at its scoped level.

- Make Labels, Label Groups, Services and IP Lists fully working, and connect them to the policy rule pickers.

- Static views (Dashboard, Cloud) and the blank Map.

- Stop: working console complete.

# Later phase (not part of this build)

Once the console works, add tasks and check scripts to the parts of the console that match the tasks used in the Foundation and Select exams. Not to be built until the working console is complete.

# Verification

- Automated headless-Chrome tests, as used for the existing lab: serve the page with the lab web server locally and drive each flow with scripted clicks and typing.

- Page-content checks, plus screenshots compared with the capture's reference screenshots.

- A smoke test that opens every menu item in the manifest and confirms each one renders a page.

- Re-run the existing pairing, cross-tab, policy and edit/remove tests after every step.

- Check scripts: syntax-checked and tested against sample state files; instruqt track validate before every push.

- After every push: commit and push to GitHub 26x-course, then a fresh Instruqt session to confirm.

# Notes

- Magic links are credentials. A magic link pasted into chat on 6 October 2026 should be treated as exposed: let it expire or have it revoked, and use a fresh one for the capture run, set as an environment variable when running the script.

- Open question: should "Block Development to Production" use an Allow rule (as now) or a Deny rule in the new lab?